## F-II Phy ON GOING
FORM - II
PROGRESS REPORT OF WORKS EXECUTED FROM CENTRAL ROAD FUND(NORMAL)
REPORT FOR THE QUARTER ENDING SEPTEMBER - 2017 (Financial figure Rs.in lakhs)
STATE:- ARUNACHAL PRADESH
Sl. No. | Name of the Work | Length(Km)/M for bridge | Amount of Administrative Approval (In Lacs) | Sanction/AA No. & Date | Technical Sanction No., date & amount. | Physical Progress |  |  | Remark
[6 empty] | Upto the end of previous year | During the year | Total Progress upto the end of the Quarter (col.7+8)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
ONGOING SCHEMES
10th PLAN(2002 - 2007)
11th PLAN(2007 - 2012)
1 | Construction of Road from Old Laiwang to Jagthung, in Tirap District, A.P. | 4.50 km | 830.64 | NH.12031/98/2015/Ar.P/CRF/NH-10 Dtd.15.06.2010 | CEAP(E/Z)/CRF-52/SEK/2015-16/444-51 dtd.24-05-2016 Rs.780.00 Lakhs | 1) JC-3.20 km 2) F/Cutting-3.20 km 3) Widening-1.300 km 4) RCC Slab cul 2 mtr span-3 Nos. 5) GSB, Gr - I - 4.450 km. | Nil | 1) JC-3.20 km 2) F/Cutting-3.20 km 3) Widening-1.300 km 4) RCC Slab cul 2 mtr span-3 Nos. 5) GSB, Gr - I - 4.450 km.
2 | Construction of 3 Nos. of RCC Bridge in between the road of CO HQ Dadam to Mukhowa Village in Tirap Distt. Arunachal Pradesh. | 45.00 mtr. (10 +10+25) | 500 | NH-12031/105/2016/Ar.P/CRF/P-8/ dtd. 3/01/2017 | No.SEK/WORKS/KSA/TS/2016-17/1450-53 Dtd.20/03/2017 for Rs. 473.98 Lakhs | - | One side foundation work of 25 mtr span bridge completed and work suspended due to monsson | One side foundation work of 25 mtr span bridge completed and work suspended due to monsson | Work in progress
3 | Construction of Namsang- Khela Road in Tirap Distt. (Ch:- 27.00 to 48.00 km). | 17.00 km | 2780 | AA No. NH-12031/103/2016/Ar.P./CRF/P-8 Dated 03-01-2017. | CEAP(E/Z)/CRF-49/Namsang- Khela/2016-17/101-108 dtd.25-04-2017 for Rs.2637.34 Lakhs | - | JC-4.00 Km FC-4.00 Km | JC-4.00 Km FC-4.00 Km | Work in progress
4 | Construction of Double Lane RCC Bridge over River Tirap to Changtalng Town in Changlang Distt. A.P. | - | 1200 | NH-12031/102/2016/Ar.P/CRF/P-8/ dtd. 03/01/2017 | CEAP(E/Z)/CRF-59/Changlang RCC Bridge/2016-17/106-14 dtd Itanagr.23-05-2017 for Rs.1099.49 Lakhs | Tender under process | Tender under process | Tender under process
5 | Construction of Road from Nongsaya Village to Mekang Miri in Namsai Distt. A.P. | 7.50 km | 1500 | NH-12031/101/2016/Ar.P/CRF/P-8/ dtd. 03/01/2017 | CEAP(E/Z)/CRF-62/2017-18/92-100 dtd.05-2017 for Rs.946.69 Lakhs | - | Tender under process | Tender under process
6 | Construction of Steel Composite Bridge over River Sissor at 14 km in Dambuk-Paglam road in Lower Dibang Valley Distt. | - | 600 | NH-12031/104/2016/Ar.P/CRF/P-8/ dtd. 03/01/2017 | SETC/CRF/RNG-7/2017-18/456-59 dtd. Tezu 06/06/2017 for Rs.569.90 Lakhs | - | Sub - Soil investigation of Bridge in progress | Sub - Soil investigation of Bridge in progress
7 | Improvement of Hunli Township road in Lower Dibang Valley Distt. A.P. | 7.41 km | 950 | NH-12031/100/2016/Ar.P/CRF/P-8/ dtd. 03/01/2017 | SETC/CRF/RNG-7/2017-18/90-93 dtd. Tezu 12/04/2017 for Rs.900.48 Lakhs | - | Tender under process | Tender under process
8 | Construction of various roads and bridges under Lekang Circle in Namsai Distt. A.P. | - | 2500 | NH-12031/98/2016/Ar.P/CRF/P-8/ dtd. 03/01/2017 | CEAP(E/Z)/CRF-63/2017-18/387-94 dtd Itanagar.06/06/2017 Rs.1758.72 Lakhs | - | Tender under process | Tender under process
9 | Construction of Improvement of Chongkham Township (10.km) in Namsai Distt. AP. | 10.00 km | 1000 | NH-12031/97/2016/Ar.P/CRF/P-8/ dtd. 26/12/2016 | SETC/CRF/NMS-6/2017-18/205-08 dtd. Tezu 27/04/2017 for Rs.947.47 Lakhs | - | Work awarded | Work awarded
10 | Construction of road from Lilong to Khimiyang (21.6 km) in Changlang District in the state of Arunachal Pradesh under CRF | 21.60 km | 2928 | NH-12031/87/2016/Ar.P/CRF/P-8/ dtd. 12/07/2017 | CEAP(E/Z)/CRF-14/SEK/2017-18/1058-66 dtd Itanagar.28-08-2017 Rs.2778.20 Lakhs | Tender finalised | Tender finalised | Tender finalised
11 | Extension of Township road at Khonsa in Tirap District HQ in AP ( Job No.CRF/Ar.P/2017-18/ 98) | 1.50 km | 483 | NH-12031/49/2017/Ar.P/CRF/P-8/ dtd. 18/05/2017 | No.SEK/WORKS/TS/2017-18/396-97 Dtd.03/07/2017 for Rs. 458.67 Lakhs | - | - | - | Awarded letter yet to be issued
| Surveyor of Works, |  | Sr. Finance & Accounts Officer, |  |  | Supdtg. Surveyor of Works, |  | Chief Engineer,
| Eastern Zone, PWD, |  | Eastern Zone, PWD, |  |  | Eastern Zone, PWD, |  | Eastern Zone, PWD,
| Arunachal Pradesh. |  | Arunachal Pradesh. |  |  | Arunachal Pradesh. |  | Arunachal Pradesh.

## F -III Fin.
FORM - III
EXPENDITURE REPORT OF ONGOING WORKS EXECUTED FROM CENTRAL ROAD FUND(NORMAL)
REPORT FOR THE QUARTER ENDING SEPTEMBER -2017 (Financial figure in lakhs)
STATE:- ARUNACHAL PRADESH
Sl. No. | Name of the Work | Job No. | Amount of Administrative Approval | Progressive total of the funds released upto end of the previous financial year | Total expenditure incurred against the work upto the end of the previous financial year | Expenditure from 1st April of the year under report to the end of the previous quarter | Expenditure during the quarter to which the return relates | Cumulative expenditure upto the end of the quarter .(Total of columns No. (6),(7),(8)) | Remark
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
ONGOING SCHEMES
10th PLAN(2002 - 2007)
A | Schemes fully funded by the Govt. of India
1 | Construction of Road from Old Laiwang to Jagthung, in Tirap District, AP. | CRF/Ar.P/2015-16/76 | 830.64 | 600 | 250 | - | - | 250
2 | Construction of 3 Nos. of RCC Bridge in between the road of CO HQ Dadam to Mukhowa Village in Tirap Distt. Arunachal Pradesh. | - | 500 | 50 | - | - | - | - | Fund alloted during 2016-17 Rs. 35.00 Lakhs surrendered
3 | Construction of Namsang- Khela Road in Tirap Distt. (Ch:- 27.00 to 48.00 km). | Job No. CRF/Ar.P/2016-17/93. | 2780 | 100 | - | - | - | - | - do-
4 | Construction of Double Lane RCC Bridge over River Tirap to Changtalng Town in Changlang Distt. AP. | - | 1200 | - | - | - | - | -
5 | Construction of Road from Nongsaya Village to Mekang Miri in Namsai Distt. AP. | - | 1500 | - | - | - | - | -
6 | Construction of Steel Composite Bridge over River Sissor at 14 km in Dambuk-Paglam road in Lower Dibang Valley Distt. | - | 600 | - | - | - | - | -
7 | Construction of Improvement of Hunli Township road in Lower Dibang Valley Distt. AP. | - | 950 | - | - | - | - | -
8 | Construction of various roads and bridges under Lekang Circle in Namsai Distt. Ap. | - | 2500 | - | - | - | - | -
9 | Construction of Improvement of Chongkham Township (10.km0 in Namsai Distt. AP. | - | 1000 | - | - | - | - | -
10 | Construction of road from Lilong to Khimiyang (21.6 km) in Changlang District in the state of Arunachal Pradesh under CRF | - | 2928 | - | - | - | - | -
11 | Extension of Township road at Khonsa in Tirap District HQ in AP ( Job No.CRF/Ar.P/2017-18/ 98 | Job No.CRF/Ar.P/2017-18/ 98 | 483 | - | - | - | - | -
|  | Total Rs. | 15271.64 |  |  |  |  | 250
Surveyor of Works, |  | Sr. Finance & Accounts Officer, |  |  | Supdtg. Surveyor of Works |  |  | Chief Engineer,
Eastern Zone, PWD, |  | Eastern Zone, PWD, |  |  | Eastern Zone, PWD, |  |  | Eastern Zone, PWD,
Arunachal Pradesh. |  | Arunachal Pradesh. |  |  | Arunachal Pradesh. |  |  | Arunachal Pradesh.